## ISSUES
ISSUES
Lifting of existing vessels over the newly installed ones.
Limited crane access to existing vessels.
Existing ground surface is gravel paving.
Overhead cables will obstruct during equipment and construction machineris access, e.g. cranes, filter vessels etc.
The copper strips may be damaged by excavation work for both filter vessels foundations and cable tranches.
Live power cables shall be protected or relocated.
There is no indication at site where these suspected cables from from.
There will be heavy vehicles going in or coming out from this junction. Also, possibly vehicle parking beside Road TP5. Construction cabins may also be place near the junction. Adjacent villegers will use this junction for access.
Villagers using the same road so concern are raised on heavy machineries passing the same road.
There is limited space for equipment laydown within MS (which include construction tools)
Security of tools and equipments, as the surrounding area is prone to theft (based on past experience).
Rubbish and construction waste may be dispose at unauthorised/ approve dumpsite.
There is only one main entrance for access into/ out the MS.

## ACTION ITEMS
ACTION ITEMS
Lifting plan to be thoroughly reviewed due to lifting over existing facilities. Steel plates to be placed over gravel paving.
Mark presence of power cables by installing warning sign posts nearby.
Conduct scanning or underground utilities detection to identify all undergrtound facilities before any work start, and produce a report for reference.
Verify the suspected underground facilities with "As-Builts" drawings and confirm at site, before start work.
Provide protection upon confirmation.
It was decided that vehicle traffic at junction of Road TP5 is not a main concern, due to all the construction works will take place about 500m away from the junction. Furthermore, a Traffic Management procedure will be part of contractor's deliverables (as per PTS 18.03.03, Contractor HSE Management) for traffic control of this project. For site office cabins, these cannot be placed in site (must be at 3KM - 5KM away) Project signboard are fixed before the entrance to the plant
Create awareness to the villagers
Meet with JKK before the construction starts place
If there is any damages during construction, the contractors will make new surfacing for the existing accessing roads
Propose csr activities to resurface the road from the main road junction to the main gate in according to existing size upon completion of project.
An area allocated just outside the MS area, i.e. on left side of access road.
Avoid any trucks or trailers to park just outside the MS area (along access road).
Allocate a specified area within MS for hand tools and construction machineries temporary storage, (without obstructing existing MS operation).
Remind potential contractors to be extra careful during site visits period.
Identify areas to temporary gather construction wastes and large waste bins may be used to temporary store it.
verify whether any approval require from local authorities(Majlis).
verify whether there is any need for a new EIA or adopt an existing PGB's EIA.
Contractor to establish construction wastes management.
An emergency access route has been identified and the route is behind the existing control building which can be only used to exit the MS.
There is an existing Panic door going into MRC area. Liase with MRC for emergency access during the working hours and also an area inside as an emergency assembly point. (the area should be barricaded to prevent any person to wonder into the plant. There may be security personnel stationed during working hours.